## MARP Projects
District | County | County Name | State Projno | ST/RD/BR Name | Typework | Route | BEGMP | MILES ( as a number) | MILES | ADT | ADT YR - YY | Con Code | Con Perf By | ADV/ AUTH Date | START CONST Date | COMPL CONST Date | Total Constr Proj $$$$ | ST | Fam Cde | PTS KEY | PO ISSUED SCHEDULED (Use NA if no PO) | PO ISSUED ACTUAL (Use NA if no PO) | CONT. (Use NA if no Contractor) | FIELDWORK START SCHEDULED | FIELDWORK START ACTUAL | FIELDWORK COMPLETE SCHEDULED | FIELDWORK COMPLETE ACTUAL | FINAL INVOICE PAID | DATE BF-150 SUBMITTED TO FINANCE
01 | 03 | BOONE | S303- 3/ - 14.12 00 | DRAWDY MOUNTAIN SITE 3 | CORR SLIDE | WV003 | 14.12 | 0.04 | 0.04 | 4900 | 00 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 270000 | AF | MA | 2020000990 | 2020-08-03 | 2020-08-03 | GSI | 2020-09-28 | 2020-09-23 | 2020-10-19 | 2020-09-18 | 2020-11-09 | 2020-11-18
01 | 03 | BOONE | S303- 94/ - 2.74 00 | SHORT CREEK SITE 2 | REP SLIDE | WV094 | 2.75 | 0.03 | 0.03 | 5600 | 18 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 370000 | AF | MA | 2020000991 | 2020-08-03 | 2020-08-03 | GSI | 2020-10-05 | 2020-09-22 | 2020-10-30 | 2020-09-18 | 2020-11-13 | 2020-12-09
01 | 08 | CLAY | S308- 19/ 1- 1.32 00 | MOORE FORK RD | CORR DRAIN, BASE, PAVE | CO019/01 | 1.32 | 1.32 | 1.32 | 100 | 18 | 07 | SF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 100000 | AF | MA | 2020000992 | NA | NA | NA | 2020-08-14 | 2020-08-14 | 2020-11-15 | 2020-09-26 | 2020-09-30 | 2020-11-18
01 | 08 | CLAY | S308- 24/ - 0.42 00 | UPPER SYCAMORE RD | REP DRAIN, REP BASE, PAVE | CO024 | 0.4 | 0.4 | 0.4 | 600 | 18 | 67 | SF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 100000 | AF | MA | 2020000993 | NA | NA | NA | 2020-09-15 | 2020-09-14 | 2020-11-15 | 2020-10-01 | 2020-12-18 | 2021-01-11
01 | 20 | KANAWHA | S320- 32/ 3- 0.00 00 | RIVERBEND RD | REP DRAIN, BASE, PAVE | CO032/03 | 0 | 1.73 | 1.73 | 1900 | 00 | 67 | SF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 275000 | AF | MA | 2020000997 | 2020-09-15 | 2020-10-08 | WV Paving | 2020-10-05 | 2020-10-05 | 2020-12-07 | 2020-10-03 | 2020-11-12 | 2020-12-09
01 | 20 | KANAWHA | S320- 43/ - 0.00 00 | FRAME RD | REP DRAIN, BASE, PAVE | CO043 | 0 | 5.33 | 5.33 | 10200 | 00 | 07 | SF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 500000 | AF | MA | 2020000995 | 2020-09-15 | 2020-10-08 | WV Paving | 2020-09-21 | 2020-09-21 | 2020-12-07 | 2020-10-09 | 2020-11-13 | 2020-12-09
01 | 20 | KANAWHA | S320- 75/ - 0.16 00 | ASHFORD RD | CORR SLIDE | CO075 | 0.12 | 0.02 | 0.02 | 2100 | 18 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 335000 | AF | MA | 2020001068 | 2020-08-03 | 2020-08-03 | GSI | 2020-09-01 | 2020-09-02 | 2020-09-25 | 2020-10-20 | 2020-12-02 | 2021-01-11
01 | 20 | KANAWHA | S320- 77/ 1- 0.00 00 | FIELDS CR RD | RESURF | CO077/01 | 0 | 5 | 5 | 1500 | 00 | 67 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 800000 | AF | MA | 2020000998 | 2020-09-15 | 2020-10-08 | WV Paving | 2020-09-08 | 2020-09-08 | 2020-12-07 | 2020-10-21 | 2020-11-10 | 2020-12-09
01 | 20 | KANAWHA | S320- 81/ - 1.00 00 | BELLE CR RD | REP DRAIN, BASE, PAVE | CO081 | 1 | 3 | 3 | 3300 | 00 | 67 | SF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 325000 | AF | MA | 2020000999 | 2020-09-15 | 2020-10-08 | WV Paving | 2020-10-07 | 2020-10-07 | 2020-12-07 | 2020-10-28 | 2020-12-02 | 2020-12-03
01 | 20 | KANAWHA | S320- 119/13- 1.35 00 | CRESTWOOD | CORR SLIDE | CO119/13 | 1.35 | 0.03 | 0.03 | 150 | 00 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 125000 | AF | MA | 2020001064 | NA | NA | NA | 2020-07-27 | 2020-07-27 | 2020-09-30 | 2020-11-06 | 2020-11-12 | 2020-12-09
01 | 27 | MASON | S327- 23/ - 0.00 00 | LEON BADEN RD | REP DRAIN, BASE, PAVE | CO023 | 0 | 3.55 | 3.55 | 1100 | 18 | 20 | SF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 165000 | AF | MA | 2020001057 | NA | NA | NA | 2020-09-14 | 2020-09-18 | 2020-11-30 | 2020-11-08 | 2020-11-12 | 2021-01-11
01 | 27 | MASON | S327- 62/ - 31.69 00 | WEST COLUMBIA | REP DRAIN, BASE, PAVE | WV062 | 31.69 | 0.25 | 0.25 | 2100 | 18 | 20 | SF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 250000 | AF | MA | 2020001055 | NA | NA | NA | 2020-10-19 | 2020-10-19 | 2020-11-30 | 2020-11-10 | 2020-12-10 | 2021-01-11
01 | 40 | PUTNAM | S340- 26/ - 5.53 00 | LIME KILN RD | CORR SLIDE | CO026 | 5.53 | 0.08 | 0.08 | 200 | 18 | 17 | DF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 640000 | AF | MA | 2020001058 | 2020-08-03 | 2020-08-03 | GSI | 2020-09-22 | 2020-09-26 | 2020-12-15 | 2020-11-12 | 2020-11-12 | 2020-11-18
01 | 40 | PUTNAM | S340- 35/ 9- 0.14 00 | SCHOWEN HILL RD SITE | CORR SLIDE(SOIL NAILS) | CO035/09 | 0.45 | 0.06 | 0.06 | 21 | 17 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 550000 | AF | MA | 2020001066 | 2020-08-03 | 2020-08-03 | GSI | 2020-08-18 | 2020-08-18 | 2020-09-21 | 2020-11-25 | 2020-12-10 | 2021-01-11
01 | 40 | PUTNAM | S340- 62/ - 9.69 00 | HOMETOWN SITE 2 | CORR SLIDE | WV062 | 9.69 | 0.1 | 0.1 | 4300 | 18 | 17 | DF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 690000 | AF | MA | 2020001060 | 2020-08-03 | 2020-08-03 | GSI | 2020-08-31 | 2020-08-28 | 2020-10-02 | 2020-11-25 | 2020-12-14 | 2021-01-15
02 | 06 | CABELL | S306- 30/ - 1.96 00 | CYRUS CREEK CULVERT 2 | REPL CULVERT | CO030 | 1.95 | 0.01 | 0.01 | 3835 | 16 | 20 | SF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 250000 | AF | MA | 2020001013 | N/A | N/A | N/A | 2020-11-07 | 2020-10-26 | 2020-11-27 | 2020-11-24 | 2020-11-30 | 2020-12-04
02 | 06 | CABELL | S306- 30/ - 2.49 00 | CYRUS CREEK CULVERT #4 | REPL CULVERT | CO030 | 2.49 | 0.01 | 0.01 | 3835 | 16 | 20 | SF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 25000 | AF | MA | 2020001046 | N/A | N/A | N/A | 2020-10-24 | 2020-10-24 | 2020-10-26 | 2020-11-29 | 2020-12-02 | 2020-12-03
02 | 06 | CABELL | S306- 30/ - 2.74 00 | CYRUS CREEK CULVERT 1 | REP CULVERT | CO030 | 2.74 | 0.01 | 0.01 | 3835 | 16 | 20 | SF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 250000 | AF | MA | 2020001048 | N/A | N/A | N/A | 2020-10-22 | 2020-10-22 | 2020-10-26 | 2020-12-08 | 2020-11-17 | 2020-12-10
02 | 22 | LINCOLN | S322- 10/ - 0.00 00 | CHAPMANVILLE - HARTS | REP SLIDE, DRAIN, SKIP PAVE | WV010 | 0 | 5 | 5 | 3100 | 18 | 17 | SF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 570000 | AF | MA | 2020001010 | 2020-08-10 | 2020-08-10 | GSI | 2020-08-14 | 2020-08-14 | 2020-12-10 | 2020-12-08 | 2020-12-02 | 2020-12-10
02 | 23 | LOGAN | S323- 10/ - 33.70 00 | CHAPMANVILLE - HARTS | REP SLIDES, DRAIN, SKIP PAVE | WV010 | 33.69 | 6.4 | 6.4 | 4800 | 18 | 17 | SF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 730000 | AF | MA | 2020001017 | 2020-08-10 | 2020-08-10 | GSI | 2020-08-14 | 2020-08-14 | 2020-12-07 | 2020-12-08 | 2020-12-02 | 2020-12-11
02 | 30 | MINGO | S330- 49/ - 0.00 00 | DELORME - WILLIAMSON | REP DRAIN, SKIP PAVE | WV049 | 0 | 18.8 | 18.8 | 1700 | 18 | 20 | SF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 1000000 | AF | MA | 2020001018 | 2020-08-10 | 2020-08-10 | GSI | 2020-08-25 | 2020-08-25 | 2020-12-07 | 2020-12-09 | 2020-12-02 | 2020-12-11
02 | 50 | WAYNE | S350- 152/ - 35.50 00 | BIG CREEK - CABELL CO LN | CORR SLIDE, REP DRAIN, GR,SKIP PAVE | WV152 | 35.49 | 9.1 | 9.1 | 15600 | 18 | 17 | SF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 1300000 | AF | MA | 2020001002 | 2020-08-25 | 2020-08-25 | GSI | 2020-08-31 | 2020-08-31 | 2020-12-10 | 2020-12-21 | 2020-12-02 | 2020-12-12
03 | 07 | CALHOUN | S307- 33/ - 0.31 00 | TRISTAN - LEATHERBARK RD | REP SLIP | US033 | 0.31 | 0.03 | 0.03 | 1700 | 19 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 450000 | AF | MA | 2020001045 | 2020-08-10 | 2020-08-10 | GSI | 2020-08-24 | 2020-08-25 | 2020-10-24 | 2020-09-18 | 2020-09-30 | 2021-10-22
03 | 18 | JACKSON | S318- 33/ - 15.60 00 | RIPLEY - GAY RD | CORR SLIP | US033 | 15.6 | 0.02 | 0.02 | 3900 | 19 | 17 | DF | 2020-08-28 | 2020-08-28 | 2020-12-28 | 300000 | AF | MA | 2020001044 | NA | NA | NA | 2020-11-01 | 2020-10-20 | 2020-12-04 | 2020-10-23 | 2020-11-04 | 2021-10-22
03 | 37 | PLEASANT | S337- 2/ - 14.96 00 | JAVA - RAVEN ROCK | CORR SLIP | WV002 | 14.96 | 0.28 | 0.28 | 5000 | 19 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 3100000 | AF | MA | 2016000567 | 2020-08-17 | 2020-08-17 | GSI | 2020-10-28 | 2020-10-27 | 2020-12-31 | 2020-11-20 | 2020-12-18 | 2021-10-22
03 | 37 | PLEASANTS | S337- 2/ - 15.51 00 | JAVA - BENS RUN RD | CORR SLIP | WV002 | 15.51 | 0.05 | 0.05 | 5000 | 19 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 400000 | AF | MA | 2020001042 | 2020-08-04 | 2020-08-05 | GSI | 2020-10-28 | 2020-11-02 | 2020-12-10 | 2020-11-20 | 2020-12-18 | 2021-10-22
03 | 43 | RITCHIE | S343- 47/ - 3.25 00 | CISCO - MACFARLAN RD | CORR SLIP | WV047 | 3.25 | 0.04 | 0.04 | 650 | 19 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 250000 | AF | MA | 2020001041 | 2020-09-15 | 2020-09-28 | BBR Drilling | 2020-11-01 | 2020-10-21 | 2020-12-04 | 2020-11-25 | 2020-12-18 | 2021-10-22
03 | 44 | ROANE | S344- 14/ 9- 0.38 00 | OAK DRIVE | CORR SLIDE | CO014/09 | 0.38 | 0.04 | 0.04 | 400 | 19 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 500000 | AF | MA | 2020001035 | 2020-08-04 | 2020-08-05 | GSI | 2020-09-30 | 2020-09-21 | 2020-12-04 | 2020-11-25 | 2021-02-15 | 2021-10-22
03 | 53 | WIRT | S353- 53/ - 0.41 00 | STANDING STONE | CORR SLIDE | WV053 | 0.41 | 0.05 | 0.05 | 1500 | 19 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 450000 | AF | MA | 2020001034 | 2020-09-17 | 2020-09-21 | GSI | 2020-11-01 | 2020-10-09 | 2020-12-10 | 2020-12-22 | 2020-12-18 | 2021-10-22
03 | 54 | WOOD | S354- 2/ - 23.91 00 | EMERSON AVE | CORR SLIDE | WV002 | 23.91 | 0.08 | 0.08 | 10400 | 19 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 750000 | AF | MA | 2020001032 | 2020-08-04 | 2020-08-05 | GSI | 2020-08-24 | 2020-08-21 | 2020-10-23 | 2021-02-26 | 2021-02-26 | 2021-10-22
04 | 09 | DODDRIDGE | S309- 13/ - 0.72 00 | MAXWELL RIDGE RD | GRADE, STABILIZE, COMPACT | WV023 | 0.72 | 8.1 | 8.1 | 50 | 19 | 10 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 80000 | AF | MA | 2020000986 | N/A | N/A | N/A | 2020-08-17 | 2020-08-26 | 2020-09-18 | 2020-09-15 | 2020-10-16 | 2020-12-18
04 | 09 | DODDRIDGE | S309- 23/ - 7.30 00 | WV 23 | SLIDE REPAIR | WV023 | 7.3 | 0.02 | 0.02 | 650 | 19 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 154500 | AF | MA | 2020000985 | 2020-08-21 | 2020-08-21 | GSI | 2020-09-10 | 2020-09-16 | 2020-10-09 | 2020-09-16 | 2020-11-04 | 2020-11-06
04 | 17 | HARRISON | S317- 11/ - 1.00 00 | WILSONBURG RD | 2" MILL & FILL ,1.5" OL | CO011 | 1 | 4.26 | 4.26 | 3600 | 19 | 07 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 1378000 | AF | MA | 2020000987 | 2020-08-21 | 2020-08-24 | JF Allen | 2020-08-17 | 2020-08-10 | 2020-11-25 | 2020-09-17 | 2020-11-05 | 2020-12-01
04 | 17 | HARRISON | S317- 24/ - 4.84 00 | MEADOWBROOK RD SLIDE | SLIDE REMEDIATION | CO024 | 4.84 | 0.04 | 0.04 | 16600 | 19 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 225476 | AF | MA | 2020000988 | 2020-08-21 | 2020-08-21 | GSI | 2020-09-22 | 2020-09-22 | 2020-10-23 | 2020-09-22 | 2020-11-03 | 2020-11-30
04 | 25 | MARION | S325- 9/ - 2.79 00 | WHETSTONE RD | 2" MILL & FILL ,1.5" O/L | CO009 | 2.79 | 1 | 1 | 450 | 19 | 07 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 325000 | AF | MA | 2020000989 | 2020-08-21 | 2020-08-24 | JF Allen | 2020-08-11 | 2020-08-11 | 2020-11-23 | 2020-10-02 | 2020-10-18 | 2020-11-30
04 | 25 | MARION | S325- 21/ - 3.75 00 | MONUMENTAL RD SLIDE | SLIDE REPAIR | CO021 | 3.75 | 0.02 | 0.02 | 1900 | 19 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 118240 | AF | MA | 2020001003 | 2020-08-21 | 2020-08-21 | GSI | 2020-10-26 | 2020-10-21 | 2020-12-01 | 2020-10-08 | 2020-10-29 | 2020-11-30
04 | 31 | MONONGALIA | S331- 7/ - 26.21 00 | CASSVILLE SLIDE | SLIDE REPAIR | WV007 | 26.21 | 0.01 | 0.01 | 3600 | 19 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 175630 | AF | MA | 2020001009 | 2020-08-21 | 2020-08-21 | GSI | 2020-08-27 | 2020-09-01 | 2020-10-09 | 2020-10-15 | 2020-10-28 | 2020-12-08
04 | 31 | MONONGALIA | S331- 7/19- 0.00 00 | BETHEL RD | 2" BASE COURSE ,1.5" OL | CO007/19 | 0 | 2.2 | 2.2 | 300 | 19 | 07 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 550000 | AF | MA | 2020001011 | 2020-08-21 | 2020-08-24 | Greer Ind. | 2020-08-13 | 2020-08-13 | 2020-11-09 | 2020-10-24 | 2020-11-25 | 2020-12-11
04 | 31 | MONONGALIA | S331- 29/ - 0.00 00 | JAKES RUN | RESURF - 1.5" O/L | CO029 | 0 | 0.66 | 0.66 | 3600 | 19 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 82500 | AF | MA | 2020001007 | 2020-08-21 | 2020-08-24 | Greer Ind. | 2020-08-13 | 2020-08-13 | 2020-11-12 | 2020-11-04 | 2020-11-16 | 2020-11-30
04 | 31 | MONONGALIA | S331- 52/ - 0.01 00 | BRAND RD | 2" BASE COURSE ,1.5" O/L | CO052 | 0 | 1.95 | 1.95 | 100 | 19 | 07 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 487500 | AF | MA | 2020001016 | 2020-08-21 | 2020-08-24 | Greer Ind. | 2020-08-19 | 2020-09-04 | 2020-12-02 | 2020-11-07 | 2020-11-04 | 2020-12-01
04 | 31 | MONONGALIA | S331- 52/1 - 0.00 00 | BOWLBY RD | 2" MILL & FILL ,1.5" OL | CO052/01 | 1 | 4.26 | 4.26 | 100 | 19 | 07 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 337500 | AF | MA | 2020001012 | 2020-08-21 | 2020-08-24 | Greer Ind. | 2020-08-24 | 2020-09-01 | 2020-12-09 | 2020-11-11 | 2020-11-25 | 2020-12-01
04 | 39 | PRESTON | S339- 39/ - 0.00 00 | RACCOON VALLEY RD | 2" MILL & FILL ,1.5" O/L | CO039 | 0 | 4.92 | 4.92 | 300 | 19 | 07 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 1599000 | AF | MA | 2020001023 | 2020-08-21 | 2020-08-25 | Stone Paving | 2020-08-17 | 2020-08-17 | 2020-11-20 | 2020-11-11 | 2020-11-27 | 2020-12-01
04 | 39 | PRESTON | S339- 50/ - 19.65 00 | GEORGE WASHINGTON HWY SLI | SLIDE REPAIR | US050 | 19.65 | 0.08 | 0.08 | 900 | 19 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 528018 | AF | MA | 2020001024 | 2020-08-21 | 2020-08-21 | GSI | 2020-10-06 | 2020-10-06 | 2020-11-25 | 2020-11-24 | 2020-12-08 | 2020-12-11
04 | 46 | TAYLOR | S346- 7/ - 0.00 00 | IRONTOWN RD | 2" MILL & FILL ,1.5" O/L | CO007 | 0 | 5.24 | 5.24 | 300 | 19 | 07 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 500000 | AF | MA | 2020001033 | 2020-08-21 | 2020-08-25 | Greer Ind. | 2020-08-06 | 2020-08-06 | 2020-10-31 | 2020-11-30 | 2020-12-03 | 2020-12-11
04 | 46 | TAYLOR | S346- 13/27- 0.24 00 | ART MOORE-SIDETRACK RD SL | SLIDE REMEDIATION | CO013/27 | 0.24 | 0.01 | 0.01 | 50 | 19 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 44600 | AF | MA | 2020001079 | 2020-08-21 | 2020-08-21 | GSI | 2020-10-20 | 2020-10-19 | 2020-12-01 | 2020-12-08 | 2020-12-10 | 2020-12-12
05 | 02 | BERKELEY | S302- 11/ - 11.71 00 | MARTINSBURG-WINCHESTER AV | RESURFACING | US011 | 11.7 | 1.55 | 1.55 | 13736 | 19 | 14 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 500000 | AF | MA | 2020001062 | 2020-08-17 | 2020-08-21 | Jeff. Asph. | 2020-10-01 | 2020-09-23 | 2020-12-01 | 2020-09-29 | 2020-10-19 | 2020-12-03
05 | 02 | BERKELEY | S302- 13/ - 1.00 00 | N TENNESSEE AVE | WIDEN, RESURFACE | CO013/27 | 1 | 0.4 | 0.4 | 4359 | 19 | 14 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 450000 | AF | MA | 2020001061 | 2020-08-24 | 2020-08-25 | Jeff. Asph. | 2020-11-16 | 2020-10-30 | 2020-12-18 | 2020-10-01 | 2020-10-15 | 2020-12-03
05 | 12 | GRANT | S312- 50/ - 0.02 00 | GORMANIA-GEORGE WASH. HWY | RESURFACING | US050 | 0 | 7.2 | 7.2 | 1488 | 19 | 14 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 975000 | AF | MA | 2020001067 | 2020-08-19 | 2020-08-25 | WV Paving | 2020-09-01 | 2020-09-01 | 2020-12-01 | 2020-11-02 | 2020-11-06 | 2021-02-08
05 | 14 | HAMPSHIRE | S314- 50/ - 10.20 00 | ROMNEY-TRUCK CLIMBING LN | RESURFACING | US050 | 10.2 | 1.35 | 1.35 | 9272 | 18 | 14 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 600000 | AF | MA | 2020001069 | 2020-08-19 | 2020-08-25 | Belt Paving | 2020-09-14 | 2020-08-25 | 2020-12-18 | 2020-11-09 | 2020-11-10 | 2020-12-03
05 | 14 | HAMPSHIRE | S314- 50/ - 25.50 00 | LOOM-TRUCK CLIMBING LN | RESURFACING | US050 | 25.5 | 1.3 | 1.3 | 5001 | 18 | 14 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 500000 | AF | MA | 2020001070 | 2020-08-19 | 2020-08-25 | Belt Paving | 2020-09-28 | 2020-09-25 | 2020-12-01 | 2020-11-20 | 2020-11-17 | 2020-12-03
05 | 16 | HARDY | S316- 220/ - 10.20 00 | MOOREFIELD DRAINAGE | DRAINAGE IMPROVEMENTS | US220 | 10.2 | 0.5 | 0.5 | 10480 | 19 | 20 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 525000 | AF | MA | 2020001074 | NA | 2020-10-05 | Central Supply Co | 2020-10-01 | 2020-09-08 | 2020-12-01 | 2020-11-20 | 2020-11-22 | 2021-01-15
05 | 19 | JEFFERSON | S319- 9/14- 0.01 00 | SHANNONDALE DRAINAGE | DRAINAGE IMPROVEMENTS | CO009/14 | 0 | 2 | 2 | 207 | 19 | 20 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 100000 | AF | MA | 2020001073 | NA | 2020-09-04 | NA | 2020-10-01 | 2020-09-14 | 2020-12-18 | 2020-12-09 | 2020-12-15 | 2021-02-08
05 | 19 | JEFFERSON | S319- 340/ - 12.00 00 | HALLTOWN-HARPERS FERRY | RESURFACING | US340 | 12 | 2 | 2 | 23179 | 18 | 14 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 930000 | AF | MA | 2020001072 | 2020-08-17 | 2020-08-21 | Jeff. Asph. | 2020-10-01 | 2020-09-29 | 2020-12-18 | 2020-12-11 | 2021-12-26 | 2021-02-08
05 | 29 | MINERAL | S329- 220/ - 8.37 00 | CUT-OFF ROAD US 220 | RESURFACING | US220 | 8.36 | 2.61 | 2.61 | 5269 | 18 | 14 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 550000 | AF | MA | 2020001071 | 2020-08-19 | 2020-08-25 | Belt Paving | 2020-09-25 | 2020-09-04 | 2020-12-18 | 2020-12-15 | 2020-11-09 | 2021-02-08
05 | 33 | MORGAN | S333- 18/ - 0.01 00 | MAGNOLIA-DETOUR RD | RESURFACING | CO018 | 0 | 5.6 | 5.6 | 144 | 19 | 14 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 600000 | AF | MA | 2020001059 | 2020-08-17 | 2020-08-25 | P&W Excav | 2020-09-07 | 2020-08-12 | 2020-12-18 | 2020-12-15 | 2021-01-03 | 2021-02-08
06 | 05 | BROOKE | S305- 27/4 - 0.00 00 | GENTEEL RIDGE | SLIDE REPAIR, 2" BASE, 1" O/L | CO027/04 | 0 | 1.5 | 1.5 | 1000 | 18 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 475000 | AF | MA | 2020001026 | 2020-08-21 | 2020-08-19 | GSI/KELLY PAV. | 2020-09-28 | 2020-08-21 | 2020-12-01 | 2020-09-18 | 2020-12-11 | 2020-12-18
06 | 15 | HANCOCK | S315- 105/ - 4.26 00 | PENNSYLVANIA AVE | 3" MILL. 2"BASE, SKID | WV105 | 4.26 | 0.33 | 0.33 | 7900 | 18 | 07 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 105000 | AF | MA | 2020001027 | 2020-08-21 | 2020-08-21 | KELLY PAVING | 2020-09-30 | 2020-09-29 | 2020-10-02 | 2020-09-22 | 2020-11-12 | 2020-12-09
06 | 26 | MARSHALL | S326- 250/ - 16.32 00 | BANE LN-PLEASANT VALLEY | SLIDE REPAIR, 2"BASE, 1" WEARING | US250 | 16.32 | 5.22 | 5.22 | 2400 | 18 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 1600000 | AF | MA | 2020001030 | 2020-08-21 | 2020-08-21 | GSI/KELLY PAV. | 2020-08-21 | 2020-08-25 | 2020-12-01 | 2020-09-30 | 2020-12-11 | 2020-12-18
06 | 35 | OHIO | S335- 40/8 - 0.00 00 | MT DECHANTAL RD | 2" MILL & FILL ,1" O/L, DRAINAGE | CO040/08 | 0 | 0.83 | 0.83 | 1800 | 18 | 07 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 345000 | AF | MA | 2020001037 | 2020-08-21 | 2020-08-31 | NLS PAVING | 2020-09-14 | 2020-09-13 | 2020-12-01 | 2020-10-19 | 2020-11-12 | 2020-12-09
06 | 48 | TYLER | S348- 23/ - 0.01 00 | ALMA-SHIRLEY | SLIDE REPAIR, 3" BASE, 1" WEARING | WV023 | 0 | 6.26 | 6.26 | 550 | 18 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 1300000 | AF | MA | 2020001056 | 2020-08-21 | 2020-08-13 | GSI/J.F.ALLEN | 2020-10-15 | 2020-08-20 | 2020-12-01 | 2020-11-09 | 2020-12-11 | 2020-12-18
06 | 52 | WETZEL | S352- 2/8 - 0.00 00 | E BENJAMIN DR +1 | 2" MILL & FILL ,1" O/L, DRAINAGE | CO002/08 | 0 | 1 | 1 | 100 | 18 | 07 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 170000 | AF | MA | 2020001040 | 2020-08-21 | 2020-08-24 | KLUG BROTH. | 2020-09-15 | 1910-09-16 | 2020-12-01 | 2020-12-04 | 2020-12-18 | 2021-01-14
07 | 01 | BARBOUR | S301- 92/ - 9.25 00 | BELINGTON-NESTORVILLE RD | RESURF(2") | WV092 | 9.25 | 5.19 | 5.19 | 1700 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 885000 | AF | MA | 2019001252 | 2020-07-31 | 2020-07-31 | JF Allen | 2020-08-03 | 2020-08-03 | 2020-08-17 | 2020-08-13 | 2020-09-29 | 2021-01-06
07 | 04 | BRAXTON | S304- 19/ - 25.07 00 | FLATWOODS-WESTON RD | RESURF(1.5") | US019 | 25.07 | 2.41 | 2.41 | 750 | 18 | 08 | CT | 2020-07-28 | 2020-09-28 | 2020-12-28 | 450000 | AF | MA | 2019001258 | NA | NA | JF Allen | 2020-10-08 | 2020-10-08 | 2020-10-30 | 2020-08-14 | 2020-10-01 | 2020-10-26
07 | 11 | GILMER | S311- 47/ - 9.41 00 | TROY-LINN RD | RESURF(1.5"), DR | WV047 | 9.41 | 3.62 | 3.62 | 750 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 720000 | AF | MA | 2020000718 | 2020-08-31 | 2020-08-25 | JF Allen | 2020-10-01 | 2020-10-01 | 2020-11-06 | 2020-08-27 | 2020-11-10 | 2020-11-18
07 | 21 | LEWIS | S321- 4/ - 3.30 00 | IRELAND-ROCK CAVE RD #2 | CORR SLIDE(PILING), RESURF(1.5") | WV004 | 3.3 | 3.19 | 3.19 | 650 | 18 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 576000 | AF | MA | 2020001052 | 2020-08-21 | 2020-08-19 | JF Allen | 2020-08-05 | 2020-08-05 | 2020-10-16 | 2020-10-16 | 2020-11-12 | 2021-01-06
07 | 21 | LEWIS | S321- 19/ - 0.00 00 | NAPIER-WALKERSVILLE RD | RESURF(1.5"), DR, GDRL | US019 | 0 | 1.6 | 1.6 | 600 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 350000 | AF | MA | 2020000720 | 2020-08-06 | 2020-08-06 | JF Allen | 2020-08-03 | 2020-08-03 | 2020-08-31 | 2020-10-28 | 2020-11-12 | 2021-01-06
07 | 49 | UPSHUR | S349- 4/ - 0.00 00 | IRELAND-ROCK CAVE RD | RESURF(1.5") | WV004 | 0 | 4.2 | 4.2 | 1200 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-28 | 759000 | AF | MA | 2019001259 | 2020-08-21 | 2020-08-19 | JF Allen | 2020-08-31 | 2020-08-17 | 2020-10-30 | 2020-10-30 | 2020-12-10 | 2020-12-10
07 | 51 | WEBSTER | S351- 20/ - 5.41 00 | WEBSTER RD | RESURF(1.5") | WV020 | 5.41 | 2.13 | 2.13 | 3000 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 450000 | AF | MA | 2019001257 | 2020-08-07 | 2020-08-13 | WV Paving | 2020-08-24 | 2020-08-14 | 2020-09-04 | 2020-11-03 | 2020-11-12 | 2020-11-18
07 | 51 | WEBSTER | S351- 20/ - 21.96 00 | WEBSTER SPRINGS-DIANA RD | RESURF(1.5") | WV020 | 21.96 | 2.74 | 2.74 | 1400 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 480000 | AF | MA | 2019001255 | 2020-08-04 | 2020-08-04 | Meadows Stone | 2020-08-11 | 2020-08-17 | 2020-11-06 | 2020-11-03 | 2020-10-20 | 2021-01-06
08 | 36 | PENDLETON | S336- 33/ - 12.07 00 | LIMESTONE-BENNETT GAP | RESURF(1.5" | US033 | 12.07 | 3.01 | 3.01 | 2000 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 600000 | AF | MA | 2020001039 | 2020-07-30 | 2020-07-30 | JF Allen | 2020-09-21 | 2020-09-26 | 2020-10-30 | 2020-08-17 | 2020-12-20 | 2020-12-29
08 | 38 | POCAHONTAS | S338- 219/ - 0.00 00 | DROOP MOUNTAIN RD | RESURF(1.5") | US219 | 0 | 0.36 | 0.36 | 1100 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 175000 | AF | MA | 2019001221 | 2020-07-30 | 2020-08-05 | WV Paving | 2020-08-24 | 2020-08-14 | 2020-11-16 | 2020-08-18 | 2020-12-13 | 2020-12-15
08 | 38 | POCAHONTAS | S338- 250/ - 5.30 00 | LITTLE RIVER CROSSING | REPL DRAINAGE STRUCTURE | US250 | 5.3 | 0.5 | 0.5 | 250 | 18 | 20 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 275000 | AF | MA | 2020001049 | NA | NA | NA | 2020-10-14 | 2020-10-14 | 2020-11-16 | 2020-10-06 | 2020-11-13 | 2020-11-17
08 | 42 | RANDOLPH | S342- 22/ - 7.02 00 | BEMIS RD | RESURF | CO022 | 7.02 | 6.87 | 6.87 | 40 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 750000 | AF | MA | 2020001050 | NA | NA | NA | 2020-08-17 | 2020-08-17 | 2020-12-18 | 2020-10-07 | 2020-12-02 | 2020-12-05
08 | 42 | RANDOLPH | S342- 37/ 8- 0.00 00 | FILES CREEK ROAD | RESURF | CO037/08 | 0 | 1.7 | 1.7 | 600 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 500000 | AF | MA | 2020001051 | NA | NA | NA | 2020-08-17 | 2020-08-17 | 2020-11-16 | 2020-10-08 | 2020-12-02 | 2020-12-05
08 | 42 | RANDOLPH | S342- 46/ - 10.74 00 | GOB PILE-ADOLPH | RESURF(2") | CO046 | 10.74 | 2 | 2 | 250 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 350000 | AF | MA | 2019001225 | NA | NA | NA | 2020-09-14 | 2020-09-28 | 2020-11-16 | 2020-11-05 | 2020-12-10 | 2020-12-29
08 | 47 | TUCKER | S347- 38/ - 0.19 00 | BARBOUR CO LI-JONATHAN RU | RESURF(1.5") | WV038 | 0.19 | 2.81 | 2.81 | 700 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 500000 | AF | MA | 2019001241 | 2020-07-30 | 2020-07-30 | JF ALLEN CO | 2020-08-13 | 2020-08-13 | 2020-10-30 | 2020-11-09 | 2021-01-08 | 2021-01-11
09 | 10 | FAYETTE | S310- 16/ - 8.04 00 | MAIN STREET EAST | IMPR DRAINAGE, RESURF | WV016 | 8.04 | 0.14 | 0.14 | 8300 | 18 | 20 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 390000 | AF | MA | 2020001038 | 2020-09-01 | 2020-09-08 | WV Paving | 2020-08-24 | 2020-08-21 | 2020-10-30 | 2020-10-01 | 2020-09-25 | 2020-11-06
09 | 10 | FAYETTE | S310- 38/ - 2.28 00 | SUMMERLEE RD | REPL DRAINAGE | CO038 | 2.28 | 0.03 | 0.03 | 950 | 18 | 20 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 200000 | AF | MA | 2020001036 | N/A | N/A | N/A | 2020-09-15 | 2020-08-12 | 2020-10-31 | 2020-10-05 | 2020-10-05 | 2020-10-22
09 | 10 | FAYETTE | S310- 60/18- 0.00 00 | LOOPS RD +1 | RESURF | CO060/18 | 0 | 3.24 | 3.24 | 350 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 640000 | AF | MA | 2019001287 | 2020-08-25 | 2020-08-26 | WV Paving | 2020-08-05 | 2020-08-05 | 2020-10-23 | 2020-10-06 | 2020-10-05 | 2020-11-06
09 | 10 | FAYETTE | S310- 61/ - 30.87 00 | TOWN OF MONTGOMERY | RESURF, IMPR DRAINAGE | WV061 | 30.87 | 0.61 | 0.61 | 4000 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 350000 | AF | MA | 2020001080 | 2020-09-10 | 2020-09-08 | WV Paving | 2020-09-01 | 2020-09-10 | 2020-11-06 | 2020-10-19 | 2020-10-09 | 2020-11-06
09 | 10 | FAYETTE | S310- 612/ - 3.05 00 | LICK FORK-CARLISLE RD | REPL DRAINAGE, RESURF | WV612 | 3.05 | 3.7 | 3.7 | 3000 | 18 | 20 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 940000 | AF | MA | 2019001324 | 2020-08-18 | 2020-08-26 | WV Paving | 2020-08-13 | 2020-08-13 | 2020-10-30 | 2020-10-21 | 2020-10-13 | 2020-11-06
09 | 13 | GREENBRIER | S313- 219/ - 0.00 00 | US 219 SB | IMPR DRAINAGE, RESURF | US219 S | 0 | 1.64 | 1.64 | 3600 | 18 | 20 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 2000000 | AF | MA | 2020001031 | 2020-09-14 | 2020-09-08 | WV Paving | N/A | 2020-08-11 | 2020-12-11 | 2020-10-23 | 2020-10-02 | 2020-11-06
09 | 32 | MONROE | S332- 12/ - 1.22 00 | PETERSTOWN-BALLARD RD | REPL DRAINAGE, RESURF | WV012 | 1.22 | 4.72 | 4.72 | 3200 | 18 | 20 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 500000 | AF | MA | 2020001029 | N/A | N/A | N/A | 2020-08-17 | 2020-08-17 | 2020-11-15 | 2020-10-23 | 2020-10-23 | 2020-11-06
09 | 32 | MONROE | S332- 219/ - 1.80 00 | PETERSTOWN-LINDSIDE RD | REPL DRAINAGE, RESURF | US219 | 1.8 | 0.03 | 0.03 | 3700 | 18 | 20 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 150000 | AF | MA | 2020001028 | N/A | N/A | N/A | 2020-10-13 | 2020-10-13 | 2020-11-06 | 2020-10-28 | 2020-10-28 | 2020-11-16
09 | 34 | NICHOLAS | S334- 19/42- 0.33 00 | FAIRVIEW HEIGHTS RD | CONST RETAINING WALL, WIDEN, PAVE | CO019/42 | 0.33 | 0.21 | 0.21 | 600 | 18 | 21 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 100000 | AF | MA | 2020001053 | 2020-09-14 | 2020-09-01 | WV Paving | 2020-09-14 | 2020-08-27 | 2020-10-26 | 2020-11-02 | 2020-10-13 | 2020-11-16
09 | 34 | NICHOLAS | S334- 39/ - 49.00 00 | MAIN ST | REPL DR, RESURF | WV039 | 49 | 0.01 | 0.01 | 3000 | 18 | 20 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 15000 | AF | MA | 2020001022 | N/A | N/A | N/A | 2020-09-28 | 2020-09-28 | 2020-10-15 | 2020-11-10 | 2020-10-05 | 2020-11-16
09 | 45 | SUMMERS | S345- 3/ - 12.48 00 | HINTON-HILLDALE RD | CORR SLIDE(PILING), RESURF | WV003 | 12.48 | 0.02 | 0.02 | 5400 | 18 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 350000 | AF | MA | 2020001021 | 2020-09-15 | 2020-09-18 | Meridian Driller | 2020-08-05 | 2020-08-05 | 2020-11-11 | 2020-11-20 | 2020-10-27 | 2020-12-08
10 | 24 | MCDOWELL | S324- 7/ - 0.00 00 | RODERFIELD-DAVY RD | PATCH & DRAIN | CO007 | 0 | 6.58 | 6.58 | 1600 | 18 | 29 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 1050000 | AF | MA | 2020001000 | 2020-08-10 | 2020-08-10 | AAA Paving | 2020-08-10 | 2020-08-06 | 2020-12-09 | 2020-09-01 | 2020-10-20 | 2020-12-15
10 | 24 | MCDOWELL | S324- 12/ 4- 0.77 00 | WARRIORMINE RD | CORR SLIDE(PILING) | CO012/04 | 0.77 | 0.02 | 0.02 | 2500 | 18 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 200000 | AF | MA | 2020001001 | 2020-08-07 | 2020-08-11 | Meridian | 2020-08-17 | 2020-08-27 | 2020-10-31 | 2020-09-10 | 2020-10-26 | 2020-11-09
10 | 28 | MERCER | S328- 11/ - 8.64 00 | MONTCALM-MCCOMAS RD | PATCH & DR | CO011 | 8.64 | 4.42 | 4.42 | 500 | 18 | 29 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 700000 | AF | MA | 2020001005 | 2020-08-10 | 2020-08-10 | AAA Paving | 2020-08-10 | 2020-08-10 | 2020-12-09 | 2020-10-02 | 2020-12-30 | 2021-01-04
10 | 28 | MERCER | S328- 112/ - 1.31 00 | BLUEFIELD - ADA | CORR SLIDE(PILING) | WV112 | 1.31 | 0.03 | 0.03 | 650 | 18 | 17 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 150000 | AF | MA | 2020000983 | 2020-08-14 | 2020-08-14 | Meridian | 2020-08-31 | 2020-08-18 | 2020-10-31 | 2020-10-06 | 2020-12-30 | 2021-01-04
10 | 41 | RALEIGH | S341- 3/ - 47.80 00 | WHITE OAK-SUMMERS CO RD | RESURF | WV003 | 47.8 | 4.8 | 4.8 | 8200 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 575000 | AF | MA | 2020001008 | 2020-08-07 | 2020-08-10 | AAA Paving | 2020-08-24 | 2020-09-02 | 2020-11-25 | 2020-11-05 | 2020-11-09 | 2020-12-09
10 | 41 | RALEIGH | S341- 41/ - 6.58 00 | PINEY VIEW-PRINCE RD | RESURF | WV041 | 6.58 | 3.94 | 3.94 | 2600 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 550000 | AF | MA | 2020001006 | 2020-08-07 | 2020-08-10 | AAA Paving | 2020-08-17 | 2020-08-14 | 2020-12-09 | 2020-11-06 | 2020-12-30 | 2021-01-04
10 | 55 | WYOMING | S355- 1/ - 0.00 00 | JESSE-RAVENCLIFF RD | RESURF | CO001 | 0 | 7.83 | 7.83 | 1100 | 18 | 08 | PO | 2020-08-28 | 2020-08-28 | 2020-12-31 | 850000 | AF | MA | 2020001015 | 2020-08-10 | 2020-08-10 | AAA Paving | 2020-08-10 | 2020-08-10 | 2020-12-09 | 2020-11-10 | 2020-12-30 | 2021-01-04
10 | 55 | WYOMING | S355- 16/ - 10.97 00 | PINNACLE CREEK BR | REP SUBSTRUCTURE | WV016 | 10.97 | 0.01 | 0.01 | 1900 | 18 | 35 | SF | 2020-08-28 | 2020-08-28 | 2020-12-31 | 150000 | AF | MA | 2020001054 | NA | NA | NA | 2020-08-31 | 2020-09-08 | 2020-11-06 | 2020-11-16 | 2020-12-30 | 2021-01-04