## Front Page
Cost Estimate For:
Project Name: | Madison RR Overpass Bridge
State Project #: | X203-17/11-0.00
Federal Project #:
County: | Boone
Prepared By: | M. White
Date: | 2010-07-13
Construction Mid-point (assumed) | 2016-03-30

## Summary
Alternatives
| 1 | 2 | 3 | 4 | 5 | 5A | 6 | 7 | 8 | 9 | 10 | 11 | 11A
Item | Near existing bridge | Near existing bridge | Near existing bridge | Near existing bridge | 350' up stream of existing bridge | 350' up stream of existing bridge | 1400' up stream of existing bridge | 3000' up stream of existing bridge | 1 mile+ up stream of existing bridge | Near existing bridge | Near existing bridge | Near existing bridge | Near existing bridge
Roadway Length (ft) | 765 | 820 | 820 | 805 | 280 | 792 | 760 | 525 | 720 | 833 | 750 | 820 | 820
Bridge Length (ft) | 335 | 280 | 280 | 280 | 340 | 340 | 470 | 385 | 280 | 267 | 350 | 280 | 300
Total Length (ft) | 1100 | 1100 | 1100 | 1085 | 620 | 1132 | 1230 | 910 | 1000 | 1100 | 1100 | 1100 | 1120
Design Speed (mph)* | 15 | 20 | 15 | 15 | 15 | 15 | 20 | 15 | 15 | 15 | 15 | 15 | 15
Maximum Grade (% rounded)** | 9.2 | 10 | 9.5 | 9.5 | 10.4 | 10 | 7 | 12.6 | 12.8 | 12 | 12 | 10 | 10
Est. Earthwork (CY) | 18510 | 20900 | 15700 | 15280 | 12690 | 15089 | 56300 | 14000 | 34400 | 13463 | 12856 | 14600 | 15900
Estimated No. of Properties Impacted | 11 | 10 | 10 | 8 | 5 | 10 | 9 | 3 | 20 | 7 | 10 | 9 | 9
Residents Required | 3 | 2 | 0 | 1 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 1 | 1
2012 Construction Cost | 3999206.1368 | 3744165.3076 | 4130738.1818 | 3390910.8764 | 3576526.2735 | 3816362.1342 | 5894471.208 | 3547665.0869 | 3476570.4374 | 3274512.8711 | 4270904.201 | 3468993.108 | 3446224.4067
(Construction Year) | (2014) | (2014) | (2014) | (2014) | (2014) | (2014) | (2014) | (2014) | (2014) | (2014) | (2014) | (2014) | (2014)
Future Value **** | 4494000 | 4207000 | 4641000 | 3810000 | 4019000 | 4288000 | 6623000 | 3986000 | 3907000 | 3680000 | 4799000 | 3898000 | 3872000
Engineering Cost | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000 | 700000
Envir. Clearance | (3 years) | (3 years) | (3 years) | (3 years) | (3 years) | (3 years) | (3 years) | (3 years) | (3 years) | (3 years) | (3 years) | (3 years) | (3 years)
(duration) Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Enviromental Clearance: NEPA $400,000 all alternatives <> Endangered Species varies $50,000 to $600,000 depending on likelyhood of finding species for given alignment (cost provided by Lovel Facemire on 11/16/09)
Right-of-Way Cost | 1110000 | 725000 | 240000 | 625000 | 140000 | 300000 | 405000 | 350000 | 670000 | 230000 | 280000 | 645000 | 720000
Utility / Railroad Cost | 475000 | 475000 | 475000 | 475000 | 475000 | 635000 | 475000 | 475000 | 475000 | 475000 | 475000 | 475000 | 470000
Mitigation Cost (6f / 4f) | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Mitigation Cost: for r/w of land, assume $40,000/acre <> $200,000 to $350,000 for permanent resident structures <> $100,000 for mobil homes
Total | 6779000 | 6107000 | 6056000 | 5610000 | 5334000 | 5923000 | 8203000 | 5511000 | 5752000 | 5085000 | 6254000 | 5718000 | 5762000 |  |  | NEPA (process includes: 2 public meetings, SHPO, wetlands/stream)
Design Concerns | Maintaining traffic during construction. Substantial R/W impacts and cost. | Maintaining traffic during construction. Creating Dead end street. Permanently reopening Franklin Street intersection with WV 17. | Maintaining D/W access for reidents. Creating Dead end street. Temporary detour cost. Tight work area. Permanently reopening Franklin St intersection with WV 17. | Maintaining Nathan St. access. | ***Substantial R/W and cost potential. Curve on southend of bridge. | ***Substantial R/W and cost potential. | ***Substantial R/W and cost potential. Traffic impact to subdivision on northside of WV 17. Grade of existing roads. | ***Substantial R/W and cost potential. Grade of existing roads. | ***Substancial R/W and cost potential. Impacts multi-lot site. | Maintaining D/W access and Nathan St. access. Tight work area. | Maintaining D/W access and Nathan St. access. Tight work area. Temporary detour costs. | Maintaining D/W access and Nathan St. access. Tight work area. | Tight work area.
* Limiting factor for design speed is vertical curves. **Maximum grade of new bridge and not sideroads or existing subdivision roads. ***Alternatives may be extended through subdivision beyond what is shown.
[11 empty] | **** Future value of construction cost using compound interest { FV=PV(1+i)^n} has been calculated from the estimate date of Fall 2012 to estimated construction midpoint, using inflation rate of 4%. | **** Future value of construction cost using compound interest { FV=PV(1+i)^n} has been calculated from the estimate date of July 2010 to construction year indicated above, using inflation rate of 5%.
[12 empty] | 4105000 | 4197000
[12 empty] | 420000 | 420000
[12 empty] | 658000 | 554166.6667
[12 empty] | 475000 | 500833.3333
[12 empty] | 1133000 | 1055000
[11 empty] | PE | 420000 | 420000
[11 empty] | R/W&UTI | 520000 | 520000
[11 empty] | CON | 4100000 | 4100000
| Alternatives 11: 5040000; Alternatives 11A: 5040000 | 2014 dollars